## Sheet1
Expected Progress
0
|  | 5 |  | 10 |  | 15 | Days
|  | End of Wk 1 |  | End of Wk2 |  | End of Wk3
Week 1 | Schedule Framework
Days | Monday | Tuesday | Wednesday | Thursday | Friday
| Proposal Set | Final Mod for Proposal/Program Menu | Program UI/Consultation | Program cat paws | Program game speed/Consultation
Week 2 | Schedule Framework
Days | Monday | Tuesday | Wednesday | Thursday | Friday
| Debugging | Debugging | Consultation | Debugging | Debugging/Consultation/Preparation for Presentation
Week 3 | Schedule Framework
Days | Monday | Tuesday | Wednesday | Thursday | Friday
| Presentation Slides | Scripts/Arrangement of presenters | Consultation/Rehearsal | Rehearsal | Presentation Day
Tasks/Duration(Days) | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday
Program Laser Pointer | [5 empty] | Expected | [6 empty] | Expected | Presentation
Program Cat Paw | [5 empty] | End | [6 empty] | End | Day
Program Menu/AI |  |  | Check by Brandon |  |  | Of | [6 empty] | Of | Assumed
Program UI | [5 empty] | Programming | [6 empty] | Presentation | Day
Program Statistics/Highscores | [5 empty] | Phase | [6 empty] | Preparations | of
Merging Project |  | Initial Compilation | Link the menu with game | Play Test & Ensure game is fluid | Consultation | [7 empty] | And | Presentation
Debugging of Project | [6 empty] | Reserved for last minute changes | [5 empty] | Project
Documentation
Presentation Preparations
Legend: | Color-Code | Contact Number
Glenn |  | 92232298
Troy |  | 91381285 |  | Note:
Brandon |  | 81119746 |  | First Monday is not included
Wei Heng |  | 97113472 |  | B = Brandon
B&T |  | - |  | T = Troy
T&W |  | - |  | W = Wei Heng
B&T&W |  | -
All |  | -